## Sheet1
Component | status | Feature | Description | difficulty | priority | blockers | notes
Studio | done | improve rotations in render view | make rotations controllable by user's mouse click & drag | 5 | 5
Studio | not needed rn | checkbox for showing mirror | allow to toggle mirror view on/off | 3 | 1
Studio |  | add an ‘eraser’ tool | use the push/pop for objects out of the array in order to erase make 'brush selection' button for eraser | 8 | 5
Studio |  | add undo-ability | have a 'short term memory', (use splice removal?) to push back in have undo/redo buttons & can also be controlled by ctr + z/ctr+shft + z | 8 | 5
Studio | not needed rn | Add Asymmetrical geometry options | As a user, I need the ability to the 2d sketch into a 3d model in my own specified incriments so that I can have full control over what my model looks like & add asymetrical geometry 1. allow for rotation of a specific amount 2. modeling in z-plane 'slices' instead of y-plane 'slices' | 21 | 3 | Production Ability P5 3D features limited | Could use vector creation to let users create curves --> pull each of these out in SVG/PNG format and turn into 3d mold geometry. (limit number of z-'slices') would also need to be able to detect what the printer could not do
Studio |  | Sculpting/Shaping tool | Allow use to move predrawn curves & morph/shape them into the look they want | 8 | 5
Studio |  | add lighting, material, etc. to renderSpace | add scene elements to make render look better allow for color choosing on material | 5 | 5
Studio |  | add Scene options in render mode